## Group member 4
To-do list
To be completed by: |  | 2025-11-23 |  | Name: Esfar, Justin, Sayantan, Fahim, Yousuf
Deadline: |  | 2025-11-23 |  | Date: 11/23/2025
Chapter 4 and 5
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-11-18 | 2025-11-18 | 2025-11-18 |  | Group discussed to review professor’s Chapter 7 assignment directions and split into pairs. Decided database (WideWorldImporters), chose Medium articles, and clarified deliverables.
95% | Research & Preparation | 2025-11-18 | 2025-11-19 | 2025-11-19 |  | Read through Chapter 7 (Beyond Fundamentals of Querying). Reviewed concepts from selected Medium articles: Window Functions & Pivot/Unpivot. Took notes for building examples.
88% | Drafting Propositions | 2025-11-19 | 2025-11-20 | 2025-11-20 |  | Brainstormed 10 total propositions. Assigned Pairs-- Esfar & Yusuf, Fahim & Sayantan, and Justin works independently.
95% | Writing Queries | 2025-11-19 | 2025-11-21 | 2025-11-21 |  | Wrote SQL queries for all 10 propositions. Debugged errors in WideWorldImporters. Rewrote pivot/unpivot queries and added simpler Example 10.
90% | Explanations | 2025-11-20 | 2025-11-22 | 2025-11-22 |  | Documented each example: what it does, how it works, why it’s special, and business importance. Added Medium article connections and NACE competencies.
95% | Group Presentation | 2025-11-21 | 2025-11-23 | 2025-11-23 |  | Finalize SQL notebook, rehearse script, record 15–20 minute video, and upload final submission. Include clear walkthrough of all 10 propositions.